## Slide 1
Workstream | 03/27 | 04/03 | 04/10 | 04/17 | 04/24 | 05/01
Dollar Tree | Discovery workshops Kickoff |  |  | Integration patterns Approvals LZ build support network & IAM LZ build approval | Process and Integration Scope approved | 
Oracle | Knowledge Session Kickoffs | Foundation workshops complete for Drop 1 Foundation Design Start |  | Oracle Provide Development Environment for MFCS | Process and Integration Scope completed Functional specs – Drop 1 | Oracle to share the configured MFCS environment
Integration Portfolio Governance (IPG) | ESL Operating Model team Engaged | Proposed Integration Patterns Identified for MVP | Integration Sessions Scheduled | MVP impacted Application integration strategy - DRAFT | Integration Strategy Approval | 
Arch Tools and Security (ATS) |  | Decision on DevOps Tooling LZ Build START (Provisional) | Dev Ops Tools built LZ Design submitted for Approval |  | Dev Env. Config/Dev Env. Released for application config | Application config Dev Ops Config Dev Env. released
Integration Pod & QA (IPODs) |  | Initial RICE list confirmation (Drop 1) Techspec template draft and review in progress | Code Review Checklist Complete |  | Oracle functional spec review begin | Data mapping sessions start
5 Week Milestones/Dependencies
Key dependencies across workstreams to ensure environments are prepared and integration development can start in week 6:
Key
Complete
At Risk
Delayed

## Slide 2: PROJECT WEEKLY STATUS: ATS MARCH 31, 2023
Path to Green
SCOPE | RESOURCES
SCHEDULE | BUDGET
Completed
On-track
Risk or delay
Critical issue or delay
EXECUTIVE SPONSOR: Bobby Aflatooni, Larry Gatta, Rick McNeely PROGRAM LEADER: Abhay Shetty / Bryan Byrd PM/lead: Rajesh Thukral
DELIVERABLES & KEY MILESTONES | DUE
Foundation Workshops | 4/7
OCI admin access | 4/10
DevOps Tools decision | 4/14
Development compartment ready | 5/8
PLANNED ACTIVITIES FOR NEXT FEW WEEKS | DUE
Connect with DT on DevOps POV and alignment, setup workshop if needed | 4/7
Schedule OCI PaaS and integration deep dive workshops with DT team | 4/12, 4/13
Resources onboarding for GG and ATP DB | 4/14
OCI Cloud Foundation and Networking workshop scheduled | 4/10, 4/11
Cloud Identity and Access Management (OCI&GCP) & Security Control Workshops scheduled | 4/17, 4/19
KEY CHALLENGES (R = Risk, I = Issue, A = Action, D = Decision) |  | OPEN DATE | OWNER | PLAN TO CLOSE | HELP NEEDED
D | DevOps Tools discussion and decision | 4/3 | Hasan, Harish K | Review ATS DevOps POV and deicide on Tools/timelines | 
A | OCI tenancy access needed w/admin rights to start foundation setup NLT 4/10 | 4/3 | Harish K | Access needed | 
KEY ACCOMPLISHMENTS | COMPLETED
Introductions with DT team members | 3/27
PaaS Use Cases Workshop Completed | 4/3
HEADLINES
ATS Foundation Workshop completed Additional Workshop scheduled with DT Infra and Integration teams Attended on-site Oracle MFCS kickoff
Period 2 Q1 |  | Period 3 Q1 |  |  |  | Period 4 Q2 |  |  |  | Period 5 Q2 | Period 5 Q2 |  |  |  | Period 6 Q2 | 
03/20 | 03/27 | 4/3 | 04/10 | 04/17 | 04/24 | 05/01 | 05/08 | 05/15 | 05/22 | 5/29 | 06/05 | 06/12 | 06/19 | 06/26 | 07/03 | 07/10
Notes: Navin+Hasan

## Slide 3: PROJECT WEEKLY STATUS: IPG MARCH 31, 2023
Path to Green
SCOPE | RESOURCES
SCHEDULE | BUDGET
Completed
On-track
Risk or delay
Critical issue or delay
EXECUTIVE SPONSOR: Bobby Aflatooni, Larry Gatta, Rick McNeely PROGRAM LEADER: Abhay Shetty / Bryan Byrd PM/lead: Rajesh Thukral
DELIVERABLES & KEY MILESTONES | DUE
IPG Kickoff | 4/10
NextGen Discovery Sessions (SC/POS) | 4/14
Approved Integration Strategy | 4/28
PLANNED ACTIVITIES FOR NEXT FEW WEEKS | DUE
Engage with EA team to understand priorities, work streams in progress and landscape for NextGen | 4/7
Integration Portfolio Governance kickoff with Enterprise Architecture team | 4/14
Prepare draft Canonical Models and Release Priority for MVP | 4/14
Prepare MVP impacted Application integration strategy - DRAFT | 4/21
Prepare Integration Strategy document, ready be presented with DT integration team by 4/12 | WIP
KEY CHALLENGES (R = Risk, I = Issue, A = Action, D = Decision) |  | OPEN DATE | OWNER | PLAN TO CLOSE | HELP NEEDED
A | Need to set regular cadence with the core IPG team to understand other ongoing initiatives – By 4/14 | 4/6 |  |  | 
KEY ACCOMPLISHMENTS | COMPLETED
Base generic entity relationship models have been identified for MVP | 4/6
HEADLINES
Engaged with Enterprise Architecture team Participated in project kickoff sessions, oracle foundation session and MVP breakout planning Integration strategy and portfolio governance planning in progress
Period 2 Q1 |  | Period 3 Q1 |  |  |  | Period 4 Q2 |  |  |  | Period 5 Q2 | Period 5 Q2 |  |  |  | Period 6 Q2 | 
03/20 | 03/27 | 4/3 | 04/10 | 04/17 | 04/24 | 05/01 | 05/08 | 05/15 | 05/22 | 5/29 | 06/05 | 06/12 | 06/19 | 06/26 | 07/03 | 07/10
Notes: Geoff

## Slide 4: PROJECT WEEKLY STATUS: IPOD/QA MARCH 31, 2023
Path to Green
SCOPE | RESOURCES
SCHEDULE | BUDGET
Completed
On-track
Risk or delay
Critical issue or delay
EXECUTIVE SPONSOR: Bobby Aflatooni, Larry Gatta, Rick McNeely PROGRAM LEADER: Abhay Shetty / Bryan Byrd PM/lead: Rajesh Thukral
DELIVERABLES & KEY MILESTONES | DUE
Finalize templates & coding standards for integrations | 4/14
Kick start data mapping sessions | 4/21
PLANNED ACTIVITIES FOR NEXT FEW WEEKS | DUE
Start data mapping discussions for COA | 4/21
Familiarize DT with templates for data mapping and technical specifications | 4/14
Follow up and finalize Oracle on functional specs drop date | 4/11
Identify the | 
KEY CHALLENGES (R = Risk, I = Issue, A = Action, D = Decision)D |  | OPEN DATE | OWNER | PLAN TO CLOSE | HELP NEEDED
D | Functional specs drop date from Oracle (Pending) | 4/5 | Eloy | 4/11 | 
D | Align on source for inbound integrations into MFCS identified (Store receipt) | 4/6 | Eloy |  | 
KEY ACCOMPLISHMENTS | COMPLETED
First round of alignment discussions on functional specs drop date from Oracle | 4/7
HEADLINES
Identified systems/POC from current landscape for Store receipt integration. Participate in Oracle familiarization sessions and understand key design decisions impacting integrations
Period 2 Q1 |  | Period 3 Q1 |  |  |  | Period 4 Q2 |  |  |  | Period 5 Q2 | Period 5 Q2 |  |  |  | Period 6 Q2 | 
03/20 | 03/27 | 4/3 | 04/10 | 04/17 | 04/24 | 05/01 | 05/08 | 05/15 | 05/22 | 5/29 | 06/05 | 06/12 | 06/19 | 06/26 | 07/03 | 07/10
Notes: Bala+Sushanth

## Slide 5: PROJECT WEEKLY STATUS: Overall ESL Program MARCH 31, 2023
Path to Green
SCOPE | RESOURCES
SCHEDULE | BUDGET
Completed
On-track
Risk or delay
Critical issue or delay
EXECUTIVE SPONSOR: Bobby Aflatooni, Larry Gatta, Rick McNeely PROGRAM LEADER: Abhay Shetty / Bryan Byrd PM/lead: Rajesh Thukral
DELIVERABLES & KEY MILESTONES | DUE
Integrated work plan | WO 4/10
Expense Forecast | WO 4/21
PLANNED ACTIVITIES FOR NEXT FEW WEEKS | DUE
Additional ATS Workshops | WO 4/10
Integration deep dive sessions | 4/12, 4/13
Finalize travel schedule | 4/14
SOW draft, WBS, and invoicing in progress | 4/14
Integrated project plan | 4/14
Expense Forecast | 4/21
KEY CHALLENGES (R = Risk, I = Issue, A = Action, D = Decision) |  | OPEN DATE | OWNER | PLAN TO CLOSE | HELP NEEDED
KEY ACCOMPLISHMENTS | COMPLETED
PTO calendar created | 4/3
Established separate RAID Log purposes | 4/5
HEADLINES
Second week on-site complete Core team onboarding complete ATS Foundation Workshop Completed SOW draft review with team RAID and integrated project plan in progress
Period 2 Q1 |  | Period 3 Q1 |  |  |  | Period 4 Q2 |  |  |  | Period 5 Q2 | Period 5 Q2 |  |  |  | Period 6 Q2 | 
03/20 | 03/27 | 4/3 | 04/10 | 04/17 | 04/24 | 05/01 | 05/08 | 05/15 | 05/22 | 5/29 | 06/05 | 06/12 | 06/19 | 06/26 | 07/03 | 07/10
Notes: Implementation timeline 24/36
Enterprise design – biz and tech deliverables
MVP?
Project leads identified – jules, Abhay, finance Sorensen
Roles for DT/FD of who will help on enterprise design

## Slide 6: Dollar Tree Status Report Update Cadence
1. All tracks must submit updates every Wednesday by 12:00 P.M. E.T.
2. Internal review on Thursday Morning E.T.
3. Submit status report to Dollar Tree every Thursday by noon E.T.
4. Report review Session with Dollar Tree stakeholders on Friday Morning E.T.
Expectations of weekly updates:
Everyone must update the Overall ESL Program Slide (Slide 1)
  High-level notes from your track (e.g., headlines, accomplishments, milestones)
Update the slide of your respective track
  ATS-Navin, Hasan, Rita
  IPG-Geoff
  IPOD/QA-Bala, Sushanth
We will have a 30-minute meeting on Thursday mornings to discuss updates from each track
To make this meeting an efficient use of our time, please make sure your entries are complete by this time!
Once our updates are finalized for the week, we will submit the slides to Rajesh by noon every Thursday
Weekly Friday morning review of Oracle, Deloitte, and Dollar Tree status report slides with Dollar Tree stakeholders and Oracle team