## Slide 1
Dollar Tree Enterprise Service Layer:
Initial Discovery Approach

## Slide 2
Overall Timeline

## Slide 3: Timeline
Proposed Development Start: March 27 2023 | March | April | May | Jun | Jul | Aug | Sep | Oct | Nov
Timeline |  |  |  |  |  |  |  |  | 
IPG – Integration Portfolio Governance |  |  |  |  |  |  |  |  | 
ATS - Arch Tools and Security |  |  |  |  |  |  |  |  | 
IPODS – Integration Pod |  |  |  |  |  |  |  |  | 
RIT – Retail system Integration and QA Testing |  |  |  |  |  |  |  |  | 
Oracle |  |  |  |  |  |  |  |  | 
Dollar Tree |  |  |  |  |  |  |  |  | 
Overall Timeline is of 8 Months considering a start on 3/27
Solution Overview
SIT
Configure & Build
Design Sprints
Sprints (4 -5 weeks each)
Dry Run 0
Dry Run 1
MVP1 Go-Live
Cutover
Steering Co Meetings
Cross-Team Meeting
Critical Check points Steering Co
Sprints
Key Activities
Deliverables
Strategies & Standards
CICD Setup and Code Review Checklist
Testing Approach & Boundary Readiness
SIT & Performance Sign Off
UAT Sign Off
Cutover Go Ahead
Functional Testing
Test scripts Preparation
UAT Exec & Cutover Prep
Performance Testing
Train The Trainer
UAT
Dry Run 2
Dry Run UAT
Cutover Plan & KT Plan
PMO
Initiate KT
Assist Cutover, Smoke test
Review Solution and test plan
Cutover Support
Review strategy and integration arch
Hypercare
Code Build and Unit Testing
Test Cycle Support
INT Prep & Exec; UAT Prep
Identify Integrations
Design Functional Spec & Inputs to Data Mapping
Execute Process Testing Cycle and Support Integration testing
Assist Cutover
Inputs to Data Mapping
Existing Process Walkthrough
Retrofit existing programs (If required)
UAT Execution
SIT Support
Assist Cutover
Support Hypercare
OCI Landing Zone Design
Dev environment ready
Devops/CICD tool setup
Test environment
CICD requirements/standards, tooling
Rita - ATS

## Slide 4
IPG

## Slide 5
Initial 4 week Discovery Plan - IPG
Empower teams to integrate effectively with current applications spread across Dollar Tree and Family Dollar, coordinating program timelines and balancing EA’s vision for DT’s future landscape
Understand timelines of ongoing NextGen initiatives
Review existing landscape
Understand Enterprise architectures vision for the future landscape
Consult with DT and Oracle teams on MVP Scope and process level data flows
Consult with enterprise architecture teams and align on current application retirement timelines
Key Discovery Activities
Agreement of Business Process Taxonomy
Scope of MVP business Processes
Data Scope / Segmentation for MVP agreed by all Partners
Partner Timelines and Resource Plans
Dependencies
NextGen initiatives with milestones
Application Inventory with dispositioning (Current & NextGen)
Draft Canonical Models for MVP Scope
Process and Data Flows for MVP scope
ATS Timeline and environment needs
Prioritized Integration Sprint Plan for POD teams
Deliverables
MVP DSD Scope will be aligned to an agreed subset of products / stores / vendors
Store Systems are not in scope for the MVP
Assumptions

## Slide 6: ATS Discovery Schedule
Phase | Activities | Owner | Start | End | Expected Outcome/ Deliverables
Discover | Hold soft kick off for IPG | Geoff/ Shankar | 03/27/2023 | 03/27/2023 | Identify key stakeholders, current system
 | Understand the current landscape, vision for future state, key stakeholders of current and NextGen Apps | Geoff/ Shankar | 03/28/2023 | 03/29/2023 | Identify the current system landscape and to be system landscape
 | Understand the NextGen apps and milestones and retirement plan for existing systems | Geoff | 03/28/2023 | 03/29/2023 | Understand the dependencies across various connect
 | Identify the dependences across NextGen apps | Geoff | 03/30/2023 | 03/30/2023 | 
 | Hold Kick off for IPG | Geoff/Shankar | 04/08/2023 |  | 
 | Prepare dependency plan for NextGen initiatives | Geoff | 04/08/2023 | 04/15/2023 | Dependency/Milestone plan
 | Conduct sessions to finalize the tool set (CICD /QA/Program management) | Geoff | 03/27/2023 | 04/ | 
Need to be updated

## Slide 7
ATS

## Slide 8
Initial 4 week Discovery Plan - ATS
Text….
Activity 1
Key Discovery Activities
Dependency 1
Dependencies
Deliverable
Deliverables
Assumption
Assumptions

## Slide 9: ATS Discovery Schedule
Phase | Activities | Owner | Start | End | Expected Outcome/ Deliverables
Discover |  |  |  |  | 
Need to be updated

## Slide 10
IPOD & QA

## Slide 11
Initial 4 week Discovery Plan – IPOD & QA
Text….
Activity 1
Key Discovery Activities
Dependency 1
Dependencies
Deliverable
Deliverables
Assumption
Assumptions

## Slide 12: IPDO & QA Discovery Schedule
Phase | Activities | Owner | Start | End | Expected Outcome/ Deliverables
Discover |  |  |  |  | 
Need to be updated

## Slide 13
Thank you
ABOUT DELOITTE
Deloitte refers to one or more of Deloitte Touche Tohmatsu Limited, a UK private company limited by guarantee (“DTTL”), its network of member firms, and their related entities. DTTL and each of its member firms are legally separate and independent entities. DTTL (also referred to as “Deloitte Global”) does not provide services to clients. In the United States, Deloitte refers to one or more of the US member firms of DTTL, their related entities that operate using the “Deloitte” name in the United States and their respective affiliates. Certain services may not be available to attest clients under the rules and regulations of public accounting. Please see www.deloitte.com/about to learn more about our global network of member firms. Copyright © 2023 Deloitte Development LLC. All rights reserved.

## Slide 14: Timelines, Activities & Deliverables –Integration POD to support Oracle Retail MVP
Capture technical requirements & data mapping with current and Retail applications stakeholders
Write lean design specifications
Perform Initial POC’s for connectivity testing
Establish CICD pipeline for Code promotions
Validate integrations in RICE list
Design & curate initial canonical models for Retail MVP
Participate in scope review sessions & Finalize scope for POD
Review Coding Standards
Review Existing Landscape
Discover
Design
Build
Approved integration scope
Data mapping and Technical Specification
Develop code build
Document test plan
Execute test scripts and conduct unit testing
Review results against agreed test cases
Batch schedule preparation
Testing/Go-live preparation
Support System integration test cycles
Support End to End test cycles
Support UAT test cycle
Support Performance testing
Participate in defect triaging and perform defect fixes
Provide inputs for cutover plan
Perform Smoke testing
Finalize hyper care approach
Post Go-live
Support Application Go Live
Post-production defect fixes
Conduct knowledge transfer sessions
Code Bundle
Unit Test Plan & Results
Cut over plan – Integration
Defect fix
Hypercare approach
Go-live report
Knowledge Transfer Documents
Timeline
Activities
Deliverables
Months
0
1
2
3
4
5
6
7
8
Discover
Iterative Design
Iterative Build
Test
Run

## Slide 15: Timelines, Activities & Deliverables – Oracle Retail MVP QA
Participate in design review sessions
Prepare Test strategy
Document system integration test scripts based on MVP process scenarios/user stories
Document End to End test scripts
Identify critical components for performance testing
Review existing and Identify test scenarios for automation
Automate scenarios identified for regression
Participate in process & MVP Scope sessions
Define QA framework & metrics
Define automation framework
Test Strategy
System Integration Test plan/scenarios
End to End test plan/scenarios
Performance test plan/scenarios
Testing/Go-live Preparation
Conduct System integration test cycles and report test results
Conduct End to End test cycles and report test results
Support UAT testing
Perform Performance testing and report test results
Review results against agreed Entry exit criteria
Defect Triaging, QA program and metrics reporting
Continue to automate scenarios identified for regression
Post Go-live
Support Go-live
Perform Smoke testing
Review production defect fix/testing
Continue to automate scenarios identified for regression
System integration test results
End to End test results
Performance testing results
Daily QA dashboard
Post-production QA metrics reporting
Discover
Design/Build
Timeline
Activities
Deliverables
Months
0
1
2
3
4
5
6
7
8
Discover
Iterative Design
Iterative Build
Test
Run

## Slide 16: 4 Weeks schedule/activities
Phase | Activities | Owner | Start | End | Expected outcome/deliverables
Discover | Collaborate with stakeholders to understand their requirements and ensure they are included in the scope of work | Functional Lead |  |  | A well-defined scope document that clearly outlines the goals, objectives, deliverables, and timelines for the project.
 | Ensure the scope is clearly defined and aligned with business goals. | Functional Lead |  |  | 
 | Review the scope document to ensure that it is technically feasible and achievable. | Technical Lead |  |  | 
 | Collaborate with the functional lead to identify potential technical risks and provide input on solutions. | Technical Lead |  |  | 

## Slide 17: 4 Weeks schedule/activities
Phase | Activities | Owner | Start | End | Expected outcome/deliverables
Discover | Finalize the Intergation Touch Points between Oracle and Legacy Applications | QA Lead (TBD) |  |  | Testing strategy document outlining the approach, scope, risks, timelines, and tools.
 | Tools and Resources that will be used for testing and reporting |  |  |  | Test plan document outlining the testing cycles, entry and exit criteria, and roles and responsibilities.
 | Identify the test data and team to support with data points |  |  |  | Test case documents outlining the scenarios, test steps, and expected results. Test execution reports detailing the status of each test cycle, including the number of test cases executed, passed, and failed. Defect reports detailing the defects identified during testing, including severity, priority, and status. Analytical reports detailing the test execution, test coverage, and defect trends. Daily QA dashboard providing a summary of the testing progress and status to stakeholders. Communication plan outlining the stakeholders, channels, and frequency of communication for Testing

## Slide 18
WK | Focus Area | Expected Outcomes | Attendees | Est. Duration
1 | Alignment Session: Kickoff | The purpose of the kick-off meeting is to formally notify all project team members that the project has begun and make sure everyone has a common understanding of the project and their roles. Explain project objectives, scope, approach, governance, project team and timeline | DT & FD Business Sponsors DT & FD Core Business and Project Team: IT, Data Governance, Merchandising/Purchasing, E-Comm, Finance, AP, Stores and DC Operations | 2 hours
1 | Familiarization Session: Foundations Accounting | Confirm and validate functional scope of the Merchandising Cloud Service (MCS) solution Validate decisions for key solution choices Identify and assess high-level business impacts Enable 60% completion of system configuration Build a greater understanding of how business users will interact with the system | DT & FD Core Business and Project Team: IT, Data Governance, Merchandising/Purchasing, E-Comm, Finance, AP | 4 hours
1 | Familiarization Session: Foundations Organizational Hierarchy |  |  | 2 hours
1 | Preparation Session: Technical Integration Prep Session | Provide an overview of MFCS integration architecture and the out-of-the-box integration catalogue Create an understanding of each integration method and how it is used to integrate within Oracle Retail and external systems Facilitate discussion about DT/FD high level integration requirements Identify potential integration constraints | DT & FD Project Team: IT | 2 hours
Sessions Planned

## Slide 19: Timelines, Activities and Deliverables – ESL IPG
Timeline & Phases
Activities
Deliverables
Laydown integration strategy inline with EA’s vision for the future
Define integration patterns
Define ESL responsibilities to service integration requests for NextGen initiatives
Establish cross initiative communication cadence to understand dependencies and flag risks
Define and catalog canonical models to service short term and long-term initiatives
Define strategy for handling PCI or other sensitive
Understand timelines of ongoing NextGen initiatives
Review existing landscape
Understand Enterprise architectures vision for the future landscape
Consult with enterprise architecture teams and align on current application retirement timelines
Discover
Define
Empower
NextGen initiatives with milestones
Application Inventory with dispositioning (Current & NextGen)
Empower integration pods to design and develop according to standards
Empower ATS team to monitor security and architectural standards
Educate project teams on integration patterns and leverage canonical models to expedite value delivery
Monitor capacity across integration pods and highlight risks to NextGen program timelines
Review and Update Application Integration Strategy
Review and Update Data Integration Strategy
Review and Update Cross Technology Project Release Plan
Update Application Inventory
Application Integration strategy
Data integration strategy (including initial canonical models)
Cross Technology Project Release Plan
Weekly IPG Status Report
Architecture Review Board (ARB) Playbook and Guidelines
Discover
Define
Empower
Months
0
1
2
3
4
5
6
7
8
Notes: Highlight how IPG will be working with QA

## Slide 20: 4 Weeks schedule/activities (contd)
Phase | Activities | Owner | Start | End | Expected Outcome/ Deliverables
Discover | Specific Data related problems or challenges Data security and privacy requirements for the project |  |  |  | Analyze existing data sources and assess their quality and relevance. Begin developing a data strategy for handling sensitive data. Finalize the design and catalog of canonical data models. Establish governance policies for the usage of the canonical data models.

## Slide 21
Week Starting | Focus Area | Expected Outcomes | Attendees | Est. Duration
27th March | Soft Kickoff | Review Short term/long term goals Scope, timeline, Roles, responsibilities alignment across teams Align on Agenda for kick-off and participants, schedule kick off | DT & FD Business & IT sponsors Enterprise Architect(s) | 2 hours
 | Familiarization sessions 1 | Understand Current landscape Identify NextGen initiatives and key milestones | Enterprise Architect(s) | 4 hours
 | Familiarization sessions 2 | Finalize the focus areas/priority list for initial weeks | Enterprise Architect(s) | 2 hours
 | Kick off Prep | Review the kick-off and alignment with core team before the actual kick-off | DT & FD Business & IT sponsors Enterprise Architect(s) | 2 hours
3rd April | Kick Off | Review Short term/long term goals Scope, timeline, Roles, responsibilities alignment across teams | DT & FD Business Sponsors DT & FD Core Business and Project Team: IT, Data Governance, Enterprise Architects, Solution Architects | 2 hours
 | Finalize Tools Session 1 | Discuss CICD tooling options and finalize | Enterprise Architects, Solution Architects | 2 hours
 | Finalize Tools Session 2 | Finalize QA tracking and automation tools | DT & FD QA team DT & FD NextGen POC | 2 hours
Sessions Planned

## Slide 22: Detailed Timelines, Activities and Milestones : ESL-ATS
Review Architecture with Key Stakeholders
Finalize Development & Test Architecture Design
Configure OCI Tenancy
Implement Identity and Access Management
Configure Network Connectivity
Validate OCI Tenancy
Infrastructure and PaaS Security Controls
Deliverables signoff
Analyze Future State Architecture
Network Design
Draft Proposed Architecture
Backup & Recovery/DR Strategy
Requirements for Identity and Access Management
Review monitoring and audit requirements
Cyber security gaps and requirements
Discover and Analyze
Design
Build Production
Deploy Platform Services (PaaS)
Secure Infrastructure & PaaS services
Environment Validation
Setup Backups, Monitoring & Auditing
Capture Sizing inputs
Finalize Production Configuration
Size Production
Finalize Production Architecture Design
Review Infrastructure & PaaS Security
Deliverables signoff
Analyze & Design
Stage 1 Development & Test
Stage 2 (Production)
Compartment
OCI Tenancy Architecture Design MVP
Network Design MVP
OCI & PaaS Security Design MVP
Build Development/Test
Deploy Platform Services (PaaS)
Secure Infrastructure & PaaS services
Environment Validation
Setup Backups, Monitoring & Auditing
Day-to-day monitoring and management
Environments management
Configuration & change management support
Performance & troubleshooting support
Cost optimization
Capacity management
DevOps, CI/CD
Backups
Access support
Documentation
Run & Maintain
Day-to-day monitoring and management
Environments management
Configuration & change management support
Performance & troubleshooting support
Cost optimization
Capacity management
DevOps, CI/CD
Backups
Access support
Documentation
Run & Maintain
Phase 1:
Discover & Analyze
Phase 2:
Design
Phase 3:
Build non-Prod
Stage 1
Phase 1:
Analyze & Design
Phase 2:
Build Prod
Stage 2
Timeline
ATS Build-out
Deliverables
Months
0
1
2
3
4
5
6
7
8
Notes: Highlight this is a working model to support Oracle Retail MVP. Refine over the period of time for other nextgen apps implementation