## Accesss Request
First Name | Last Name | Deloitte Email | Mobile contact
Balasubramanian | Kannan | bkannan@deloitte.com | 6825593861
Shankaran | Srinivasan | shsrinivasan@deloitte.com

## Meetings planned
Week | Track | Focus Area | Expected Outcomes | Attendees | Inputs Required | Deloitte POC | Est. Duration | Status (Scheduled) | Comments
2023-04-03 | IPG | Supply Chain | Supply Chain Project Scope & Timing | Yugander, Frans, Kirin, Bala |  | Geoff Lyle | 1 hr
Discuss methodoodly, tools, process
Application Landscape
Legacy Sources and potential overlap
2023-04-03 | IPG | POS | POS Project Scope & Timing | Yugander, Frans, Kirin, Bala |  | Geoff Lyle | 1 hr
Discuss methodoodly, tools, process
Application Landscape
Legacy Sources and potential overlap
2023-04-03 | IPG | Oracle MVP | Roles and Responsibilities for OCI | Jaco, Pete, Hassan, Bala |  | Geoff Lyle | 1 hr
RICS Scope and Reqs for ESL
Ownership of Integration components
2023-04-03 | IPG | DT Method | Review any Methodology / Tools in place | Shaina, Yugander Shankar, Bala |  | Geoff Lyle | 1 hr
Introduce capabitity matrix
Review Sample context diagrams
Review Program scope and timing
2023-04-10 |  | IPG Method Kickoff | IPG Method Overview | TDB, All key stakeholders |  | Geoff Lyle | 2 hr
High Level Application Scope and Timing
Integration Strategies
Key environment and architectural concepts

## Clarifications needed from DT
Week | Track | Clarifications | Status (Open/Closed) | Comments
2023-03-27 | IPG | Ownership of SC, POS, MVP Tracks
2023-03-27 | ATS
2023-03-27 | IPOD, QA

## Expected outcome by week
Week | Track | Expected outcome | Comments
2023-04-03 | IPG | Aligned on scope of projects currently inflight and high level timelines
Identify scope of programs and potential competing / overlapping requirements from Legacy systems
Align on toolsets / methods, adopt any in place cataloging and methods
Set schedule for ESL Workshops and IPG Method overview
Identify owners and meet with SC, POS, Merch Leaders
Preliminary ESL Canonical Data Model needs by tracks
Preparation for IPG Kickoff
2023-03-27 | ATS
2023-03-27 | IPOD, QA