## Sheet1
Task |  |  |  | Duration | Start | Finish | Predecessors
Discover
Nextgen Timeline
|  | Merchandise Project Discovery |  |  | 2023-04-03 | 2023-04-14
|  | Supply Chain Project Discovery |  |  | 2023-04-03 | 2023-04-14
|  | Stores Project Discovery |  |  | 2023-04-03 | 2023-04-14
Document Application Landscape
|  | Current Landscape |  |  |  | 2023-04-14
|  | Future State vision |  |  |  | 2023-04-21
IPG Tools and Modeling POC
|  | Define Toolset for Data Modeling |  |  |  | 2023-04-14
|  | Integrated Plan Approved |  |  |  | 2023-04-21
|  | Approve Integration Strategy |  |  |  | 2023-04-28
|  | IPG Inetgration Flow POC |  |  |  | 2023-05-05
Integration Governance Process
|  | IPG Kickoff |  |  |  | 2023-04-21
|  | Establsih IPG reivew proceess |  |  |  | 2023-05-28
|  | Agree IPG Calendar |  |  |  | 2023-05-05
Design
MVP
|  | Define Domain Canonical Models for MVP |  |  |  | 2023-04-21
Merch Hierarchy
Org Hierarchy
Suppliers
Stores
Items
Purchase Orders
Receipts
DSD Receipts
Enterprise Canonical Models
|  | Define Conceptual Models for Enterprise Design |  |  |  | 2023-05-05
|  | Define Logical model for Future State |  |  |  | 2023-05-05
|  | Draft Domain Canonical Models for Logical Entities |  |  |  | 2023-05-12
Foundation Data
Core Merchandise
Price and Promotion
Space & Assortment Planning
Supply Chain
Sales Transactions
Stores Processes
People
| ESL Release Strategy |  |  |  |  | 2023-05-26
Identify Integration Rice objects by Functional Area
Develop Logical Sprint plan to Support Enterprise Design
Identify Cross proejct depencioes with logical models
Draft Inetrgated Milestone and Release Plan
Empower |  |  |  |  | 2023-05-29 | 2023-09-29
Approve Domain Canonical Models
Review and Update IPOD Development and Capacity Plans
Review and Update Application Integration Staraegy
Revie and Update Daat Integration Strategy
Review and Update Cross Technology Project Release Plan
Update Application Inventory