## Slide 1: PROJECT WEEKLY STATUS: IPG MARCH 31, 2023
Path to Green
SCOPE | RESOURCES
SCHEDULE | BUDGET
Completed
On-track
Risk or delay
Critical issue or delay
EXECUTIVE SPONSOR: Bobby Aflatooni, Larry Gatta, Rick McNeely PROGRAM LEADER: Abhay Shetty / Bryan Byrd PM/lead: Rajesh Thukral
DELIVERABLES & KEY MILESTONES | DUE
NextGen Discovery Sessions (SC/POS) | 4/14
IPG Kickoff | 4/21
Approved Integration Strategy | 4/28
PLANNED ACTIVITIES FOR NEXT FEW WEEKS | DUE
Integration Portfolio Governance Introduction with Enterprise Architecture team | 4/7
Engage with APP owners to understand priorities, work streams in progress and landscape for NextGen | 4/14
Prepare draft Canonical Models and Release Priority for MVP | 4/14
Prepare MVP impacted Application integration strategy - DRAFT | 4/21
Prepare Integration Strategy document, ready be presented with DT integration team by 4/12 | WIP
KEY CHALLENGES (R = Risk, I = Issue, A = Action, D = Decision) |  | OPEN DATE | OWNER | PLAN TO CLOSE | HELP NEEDED
A | Need to set regular cadence with the core IPG team to understand other ongoing initiatives – By 4/14 | 4/6 |  |  | 
KEY ACCOMPLISHMENTS | COMPLETED
Base generic entity relationship models have been identified for MVP | 4/6
HEADLINES
Engaged with Enterprise Architecture team Participated in project kickoff sessions, oracle foundation session and MVP breakout planning Integration strategy and portfolio governance planning in progress
Period 2 Q1 |  | Period 3 Q1 |  |  |  | Period 4 Q2 |  |  |  | Period 5 Q2 | Period 5 Q2 |  |  |  | Period 6 Q2 | 
03/20 | 03/27 | 4/3 | 04/10 | 04/17 | 04/24 | 05/01 | 05/08 | 05/15 | 05/22 | 5/29 | 06/05 | 06/12 | 06/19 | 06/26 | 07/03 | 07/10
Notes: Geoff