## Slide 1: Secure Store Kickoff
March 7, 2018

## Slide 2: Secure Implementation Approach
Ollies Solution Overview
Project Planning
Client Services
Ollies Project Roles
Projected Timeline
What we need from you to get started

## Slide 3: Ollie’s Secure Store Solution
Secure Store v5 is an Exception Based Reporting System designed to assist Loss Prevention and Store Operations in identifying anomalies at point of sale
The Secure application will receive daily batch feed of POS sales data, store and item master data, Employee reference data and an additional feed of returns data from the Ollie’s Refund management system
The secure application will retain twelve months of detailed transactional data to support Exception Base Reporting on sales data transactions for approximately 271 retail locations
Configuration of the base Appriss Retail Enterprise Case management application is also included in the scope of the project
3

## Slide 4: Project Planning
Analyze and Determine source for POS data - Determine the best approach to source your POS data that will drive the Secure application.
Identify additional data feeds that are in scope for the project
Establish frequency and volume of each data source
Complete a preliminary sizing analysis to estimate the amount of storage required and confirm the retention estimates
Determine Infrastructure needs and estimate the timeline for procurement and availability date.
The typical deployment timeline for a Secure Store engagement is 18 – 20 weeks from the technical kickoff. With data mapping activities already underway, we will work with the Ollie’s team to develop the detailed project plan, identify roles and responsibilities , agree project dependencies and delivery milestones to keep the project on schedule.

## Slide 5: Application Configuration and Set up
After Receiving Sample data and preforming the initial mapping exercise; Appriss Retail will assist Ollie's in establishing two application environments accessible to business users:
Non Production / QA
Scaled Down environment for Initial setup and Data Validation
Supports Strategy Discussions
Application Configuration of Roles, Permissions, Portals
Development of Operational work flow
Test and Patch environment on going
Production
Full scale – All stores twelve months of data (or as much history as can be provided)
Final User acceptance Testing
Ongoing Live environment
9

## Slide 6: Client Services
Loss Prevention Strategy Sessions – Develop a full understanding of the LP structure, Establish the Risk Dictionary and strategize how Secure is going to be integrated into loss prevention processes.
Operational Review – Appriss Retail will run through a series Customer and Non Customer facing transaction sets to test System Functionality, Policy, and Procedure in the following areas:
  Price Modifications
  Refunds / returns / exchanges
  Line Voids / error corrects
  Post Voids
  Transaction suspend / resume / cancel
  Coupon / Other Discounts
  No sales / Open Drawer events
  Manager overrides / Policy
  Velocity Controls / Limits

## Slide 7: Define Process & Develop the Risk Dictionary
A standard set of risk templates are evaluated with the Client Services team during offline strategy session to establish the starting point for the application configuration
The predefined Analyst & Investigator roles in the Secure application are configured for the Ollie’s application.
The operational workflow for Secure within your organization is explained.
Dashboards for each of the roles are reviewed.
Secure receipt view and data naming conventions are configured
Data Validation begins on the QA system with live data
The Enterprise Case management configuration is completed
User Training and Ongoing support is delivered by Client Services
Preliminary Instant Analytics are agreed and configured to begin delivering work items to the investigative flow.

## Slide 8: Ollie’s Project Roles
Role | Activities
Business Team -Project Sponsor -System Administrator -AP Subject Matter Experts | Structure of the business team is dependent on the organizational structure, however a full time dedicated business team sponsor / super user and subject matter experts should be involved form the outset
Project Manager | Scheduling and coordination of deliverables Communication with Business and Appriss Retail Team Status reporting and Issue resolution
Point of Sale Developer | Identify Point of Sale Data Source & Modifications necessary for External Sharing Provide Point of Sale Technical Specification Develop POS Tlog Extract and schedule delivery via SFTP Issue resolution
Integration Developer | Identify Data source for employee, item, store data Provide Technical specification of the data extracts Develop extracts and schedule delivery via SFTP
Networking | Establish SFTP connectivity Schedule jobs to deliver POS and Master data extracts
12

## Slide 9: What we need from you
POS Specification documents
  Defines the format of the POS data file/extract (e.g. TLog documentation/POS Pullback documentation, etc.)
  Any other system documentation / Data definition documents
Cashier training documentation and other operational procedures
  This covers the tasks that a cashier can perform
Samples of POS and Returns data
  Sample set of representative transactions (should cover the functionality that the cashiers can perform, e.g. discounts, coupons, employee discounts, etc.)
  Matching receipts for those representative transactions
Full week of all stores’ sales in the same format
  this is used for testing mapping logic and for determining special cases or any other anomalies
Samples and specifications for all reference data feeds