Sprint 6 Plan Update

Eva — Program Manager  |  February 28, 2026

Classification: INTERNAL

# Executive Summary

Sprint 5 is COMPLETE. Sprint 6 scope was locked February 27 with two parallel tracks: Track 1 (Protocol Pipe) and Track 2 (Canary Slim). The Heartbeat pipeline code is built (21 new files, 7/7 smoke tests), and the sandbox integration gate has been cleared — 26 real Square webhooks received and processed with HMAC signature verification passing. The Foundation Layer (B-068) is fully delivered across all five lanes. The single gate to production heartbeat is Jeffe providing production Square credentials. We are at a natural code branch point — Sprint 5 baseline is clean, Sprint 6 TSP code is a significant new layer that should be committed to a dedicated branch.

# Sprint 5 Closeout

Sprint 5 (Integration Validation) is fully complete. All five phases delivered:

| Phase | Deliverable | Status | Verified |
| --- | --- | --- | --- |
| Phase 1 | Stack: Docker, Flask, PostgreSQL, migrations | DONE | iMac + Mac Mini |
| Phase 2 | Schema: Alembic on real PostgreSQL, 22 triggers, hash chain | DONE | Commit 5effb5e |
| Phase 3 | Data: Seed script, Level B demo data loaded | DONE | Offset Coffee data |
| Phase 4 | Tests: 541 pass / 0 fail / 0 errors / 216 skipped | DONE | Dev loop CLEAN |
| Phase 5 | Clickthrough: Today’s View, Process 4 wizard, role gating | DONE | QA stack live |

Test baseline at Sprint 5 close: 541 pass / 0 fail / 0 errors / 216 skipped. Last commit: 72d0082 (Level B demo stack). Branch: alpha-clean.

# Sprint 6 Status — Two Parallel Tracks

## Track 1: Protocol Pipe (End-to-End Evidence on Chain)

Objective: One Square event → Canary catches → seals → inscribes → receipt. The full vertical slice that proves the protocol.

| # | Component | Existed? | Status | Owner | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Square OAuth 2.0 flow | No | DONE | Jeremy | Self-auth for Phase 1 — working |
| 2 | Webhook receiver + HMAC verification | Partial | DONE | Jeremy | 26 real webhooks, all 200 OK |
| 3 | Chirp rule: refund > $10 | Yes | DONE | — | Sprint 5 rule engine |
| 4 | Evidence seal (Sub 1 — PostgreSQL) | Yes | DONE | — | Sprint 5: 22 triggers + hash chain |
| 5 | TSP-01 Webhook blueprint + stream publisher | No | DONE | Jeremy | XADD to Valkey Streams |
| 6 | TSP-03 Sub 1 consumer (seal worker) | No | DONE | Jeremy | BYTEA chain hash, advisory locks |
| 7 | TSP-05 Sub 3 Merkle batch + mock inscription | No | DONE | Jeremy | 100-event or 10-min batch |
| 8 | TSP-07 Receipt endpoint | No | DONE | Jeremy | Query by hash or event_id |
| 9 | Inscription bridge (OrdinalsBot API) | No | PENDING | Jeremy | Mock in place — live API Sprint 7 |
| 10 | Production webhook subscription | No | WAITING | Jeffe | Needs production credentials |

Track 1 Assessment: 8 of 10 components built. Sandbox integration validated end-to-end. The pipe works. Two items remain: (1) production credentials from Jeffe (15-minute action), and (2) live inscription bridge swap from mock to OrdinalsBot API (Sprint 7 scope). Track 1 is effectively done for Sprint 6.

## Track 2: Canary Slim (Beachhead Momentum)

| # | Deliverable | Status | Owner | Notes |
| --- | --- | --- | --- | --- |
| 1 | B-032: Square Developer + Merchant accounts | RESOLVED | Jeffe | Canary authorized as marketplace app |
| 2 | B-065-A: Square SDK repos cloned + indexed | RESOLVED | Jeremy | 4 repos, 5,539 files, v44.0.1 |
| 3 | B-065-B: Webhook subscription automation | RESOLVED | Jeremy | Full SDK CLI built |
| 4 | B-036: Square SDK → CRDM alignment audit | WAITING | Jeremy | Gates Tom B-035 DDL |
| 5 | B-066: Condor SDK review + TSP coding standards | IN PROGRESS | Condor | Gates Jeremy next TSP session |
| 6 | B-067: Square Capability Dashboard | IN PROGRESS | Condor+Jeremy+Qwen | 3-lane parallel build |
| 7 | Chirp Config MVP (1 page, 1 merchant) | PENDING | Art + Jeremy | After B-066 + B-067 |

# Foundation Layer (B-068) — ALL FIVE LANES COMPLETE

| Lane | Deliverable | Owner | Status | Key Output |
| --- | --- | --- | --- | --- |
| A | Partition architecture | Tom | DELIVERED | DDL templates |
| B | Blueprint v2.0 tokenization | Condor | DELIVERED | 178 tokens |
| C | Locale + vocabulary JSON packs | Condor | DELIVERED | 3 JSON files |
| D | Vocabulary schema (merchant_vocabulary) | Tom | DELIVERED | DB schema |
| E | White paper | PhD | DELIVERED | Thesis document |

Minor remaining step: Tom confirms Lane D schema accommodates full 32-token vocabulary set from Condor’s Token Registry. One-session reconciliation.

# Resolved Since Last Eva Update (Feb 26)

| ID | Blocker | Resolved By | Date |
| --- | --- | --- | --- |
| B-028 | GrowDirect company website | Jeffe | Feb 27 |
| B-032 | Square Developer + Merchant accounts | Jeffe | Feb 27 |
| B-046 | elJeffe business model documentation | ALX | Feb 27 |
| B-048 | card_fingerprint scope (network-universal) | Jeffe directive | Feb 27 |
| B-052 | MVP rethink — parallel tracks locked | Jeffe + ALX | Feb 27 |
| B-059 | TSP PRD revision cycle (21 issues, 6 passes) | Condor + PhD | Feb 27 |
| B-060 | TSP Consolidated Review v1.0 | ALX | Feb 27 |
| B-061 | Key Custody — Lightning only via Strike | Jeffe | Feb 27 |
| B-065-A | Square GitHub repo scan | Jeremy | Feb 28 |
| B-065-B | Square webhook subscription automation | Jeremy | Feb 28 |
| B-068 | Foundation Layer — all 5 lanes | Tom + Condor | Feb 28 |

12 blockers resolved in 48 hours. This is the most productive stretch since project start.

# Code Branch + New Baseline Assessment

Current Git state on alpha-clean branch:

- Last commit: 72d0082 — Level B demo stack (Today’s View + Process 4 wizard + seed script)

- Uncommitted modified files: 13 files (registry.py, session_factory.py, models, compose files, requirements.txt, valkey.conf, wsgi)

- Untracked new files: ~15 files (TSP blueprints, consumers, migrations 004–006, models, evidence_chain, webhook manager, smoke tests, entry points)

- Square SDK repos: square/ directory (4 repos, 5,539 files) — should be .gitignored, not committed

## Recommendation: Branch + Commit + Tag

- Tag current HEAD as Sprint 5 baseline: git tag sprint-5-baseline 72d0082 — marks the clean Sprint 5 state. This is the rollback point.

- Add square/ to .gitignore: SDK reference repos don’t belong in the Canary codebase. 5,539 files of vendor code.

- Create Sprint 6 branch: git checkout -b sprint-6-tsp — all TSP pipeline work goes here. Isolates Sprint 6 changes from the proven Sprint 5 base.

- Commit TSP pipeline code: Stage all 28 files (13 modified + 15 new). Single commit: feat(sprint6): TSP heartbeat pipeline — webhook, seal, Merkle, receipt

- Push to origin: Both the tag and the new branch. Remote state matches local.

Why now: The TSP pipeline is a significant architectural layer (21 new files, 3 new migrations, new Valkey Streams config, new model package). It’s validated (7/7 smoke, 26 real webhooks) but not yet integration-tested against the full Docker stack. Branching now gives us a clean rollback to Sprint 5 if integration surfaces issues, while preserving all Sprint 6 work. This is textbook branch hygiene.

# Factory Process Gate Status

| Deliverable | Current Gate | Status | Owner | Blocker |
| --- | --- | --- | --- | --- |
| TSP Heartbeat Pipeline | ASSEMBLY (Stage 3) | IN PROGRESS | Jeremy | Production creds |
| Square Capability Dashboard | PARTS (Stage 2) | IN PROGRESS | Condor+Jeremy+Qwen | None |
| Foundation Layer (B-068) | QC (Stage 4) | DELIVERED | Tom reconciliation | Minor |
| War Chest / Investor Site | QC (Stage 4) | WAITING | Syd sign-off | Syd availability |
| Chirp Config MVP | BLUEPRINT (Stage 1) | PENDING | Art + Jeremy | B-066 + B-067 first |

# Sprint 6 Timeline Estimate

### Track 1: Protocol Pipe

- Production heartbeat: 1–2 days after Jeffe provides production credentials. Jeremy has all tooling ready.

- Docker integration test: 1 day. Run Alembic migrations 004–006, start Flask + Sub 1 + Sub 3 workers, verify full pipe in Docker.

- End-to-end proof with real TX: Same day as production heartbeat. Jeffe’s phone triggers transaction → webhook → seal → mock inscription → receipt.

- Estimated delivery: March 3–4, 2026 (contingent on production credentials this weekend)

### Track 2: Canary Slim

- B-066 (Condor SDK review): 1 session, dispatched. Delivers TSP Coding Standards for Jeremy.

- B-067 (Capability Dashboard): 3 parallel lanes (Condor map, Jeremy API module, Qwen dashboard). 2–3 sessions total.

- Chirp Config MVP: Follows B-066/B-067. Art (design) + Jeremy (build). 1 week after dependencies clear.

# Top 3 Risks to Sprint 6 Delivery

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| 1 | Production credentials delayed | MEDIUM | HIGH | Jeffe action — 15 min in Square Dashboard. ALX to surface. |
| 2 | Docker integration uncovers issues in TSP migrations | MEDIUM | MEDIUM | Sprint 5 baseline tag = clean rollback. Jeremy fixes forward on sprint-6-tsp branch. |
| 3 | Context window costs escalating on multi-session builds | HIGH | MEDIUM | Consolidate sessions. Avoid compaction-driven re-hydration. Feb 27 s5 cost $130 on context replay alone. |

# Timelog Enforcement Check

Checked Documents/timelogs/2026/02-February/daily/:

- Feb 28: 2 entries (Jeremy B-065, Condor B-068 Lanes B+C) — LOGGED

- Feb 27: 6 entries (Syd/PhD dispatch, B-058 War Chest, War Chest v2.5 build, TSP PRD review, B-059 work order, Jeremy Heartbeat build) — LOGGED

- Assessment: All sessions since Feb 27 have timelog entries. No gaps detected. B-026 (skill port to Cowork) still open but manual process is working.

# Bottom Line

Sprint 6 is ahead of schedule. Track 1 is functionally complete pending one 15-minute Jeffe action. Track 2 is in active build with no blockers. The Foundation Layer is done. The War Chest is built and awaiting legal sign-off. This is the right moment to cut a code branch, tag the Sprint 5 baseline, and commit the TSP pipeline to a clean Sprint 6 branch. The team has earned a new baseline.

Prepared by ALX (Chief of Staff) on behalf of Eva (Program Manager)

February 28, 2026