WYOMING DAO LLC

FILING CHECKLIST & TIMELINE

GrowDirect DAO LLC

Prepared: February 2026 | Contact: gclyle@growdirect.io | 310-905-9272

# Phase 1: Pre-Filing Requirements

| Item | Status | Owner | Deadline | Notes |
| --- | --- | --- | --- | --- |
| Choose WY registered agent | ACTION NEEDED | Jeffe/Atty | Before filing | Must have WY physical address |
| Finalize entity name search | IN PROGRESS | Attorney | Before filing | Verify GrowDirect DAO LLC is available |
| Confirm organizer info | READY | Jeffe | Done | Geoffrey C. Lyle, gclyle@growdirect.io |
| Review Articles of Org | READY | Attorney | Before filing | Draft complete in this package |
| Review Operating Agreement | READY | Attorney | Before filing | Draft complete in this package |
| Securities counsel review | ACTION NEEDED | Attorney | Before filing | GROW token Howey analysis needed |
| Review smart contract | READY | Attorney | Before deploy | Draft in package; needs audit |

# Phase 2: Filing with Wyoming Secretary of State

## Required Filing Documents

- Articles of Organization for DAO LLC (Form available at sos.wyo.gov)

- Consent of Registered Agent (signed by the Wyoming registered agent)

- Filing Fee: $100 (check or online payment)

## Filing Methods

Online: https://wyobiz.wyo.gov (recommended, fastest processing)

Mail: Wyoming Secretary of State, Herschler Building, 122 W. 25th St., Suite 100, Cheyenne, WY 82002-0020

In Person: Same address as above

Processing Time: Online filings typically processed within 1-3 business days

## Filing Fee Schedule

| Fee Type | Amount | When Due |
| --- | --- | --- |
| Articles of Organization filing | $100 | At filing |
| Annual Report (minimum) | $60/year | Anniversary date |
| Annual Report (asset-based) | $0.0002 per $ of WY assets | If > $300K WY assets |
| Registered Agent (third-party) | $25-$125/year | Annual renewal |
| Name Reservation (optional) | $50 | Before filing (120 days) |
| Articles Amendment (smart contract) | $50 | Within 30 days of filing |
| Certificate of Good Standing | $5 | As needed |

# Phase 3: Post-Filing (Within 30 Days)

| Item | Status | Owner | Deadline | Notes |
| --- | --- | --- | --- | --- |
| Deploy smart contract | ACTION NEEDED | Jeremy | 30 days post-filing | Audit first; deploy to mainnet |
| File Articles Amendment | ACTION NEEDED | Attorney | 30 days post-filing | Add smart contract address ($50) |
| Obtain EIN (IRS) | ACTION NEEDED | Attorney/CPA | Immediately | IRS Form SS-4, free, online |
| Open business bank account | ACTION NEEDED | Jeffe | After EIN | Mercury, Relay, or local bank |
| Set up multi-sig wallet | ACTION NEEDED | Jeremy | After deploy | 2-of-3 Gnosis Safe recommended |
| File BOI Report (FinCEN) | ACTION NEEDED | Attorney | 30 days of formation | Beneficial Ownership Info |
| State business license (if needed) | ACTION NEEDED | Attorney | Varies | Check WY local requirements |

# Phase 4: Ongoing Compliance

| Obligation | Frequency | Due Date | Notes |
| --- | --- | --- | --- |
| Wyoming Annual Report | Annual | Formation anniversary | Min $60; file online at wyobiz.wyo.gov |
| Federal Tax Return | Annual | March 15 / April 15 | Depends on tax election; consult CPA |
| BOI Report Updates | As needed | 30 days of change | Update FinCEN on ownership changes |
| Registered Agent Renewal | Annual | Per agent contract | Maintain WY physical address |
| Smart Contract Upgrades | As needed | Per governance vote | Log all upgrades on-chain |
| Operating Agreement Amendments | As needed | Per supermajority vote | Keep executed copies |
| Securities Compliance | Ongoing | Continuous | Monitor token holder count and activity |

# Estimated Formation Costs

| Cost Item | Low Estimate | High Estimate |
| --- | --- | --- |
| Wyoming SOS Filing Fee | $100 | $100 |
| Registered Agent (Year 1) | $25 | $125 |
| EIN Application | $0 | $0 |
| Articles Amendment (smart contract address) | $50 | $50 |
| Smart Contract Security Audit | $5,000 | $25,000 |
| Attorney Review of Full Package | $2,500 | $7,500 |
| Securities Counsel (Howey Analysis) | $3,000 | $10,000 |
| Tax Counsel (Entity Election) | $1,000 | $3,000 |
| BOI Report Filing | $0 | $0 |
| TOTAL ESTIMATED RANGE | $11,675 | $45,775 |

COST NOTE: The actual filing with Wyoming SOS is very affordable ($100 + $25-125 registered agent). The bulk of cost is professional review: attorney, securities counsel, tax counsel, and smart contract audit. These are strongly recommended but the filing itself can proceed while audits are conducted — the 30-day window for the smart contract address amendment provides time for the audit.

# Key Contacts

Organizer: Geoffrey C. Lyle

Email: gclyle@growdirect.io

Phone: 310-905-9272

Wyoming Secretary of State: 307-777-7311

Online Filing: https://wyobiz.wyo.gov

Mailing Address: 122 W. 25th St., Suite 100, Cheyenne, WY 82002