CANARY

EARLY WARNING LP

MVP Scope & Sprint Plan

Path to Square Marketplace Listing

Prepared by:  Canary LP / GrowDirect

Date:  February 2026

Version:  1.0

Audience:  Square App Marketplace Review Team

Classification:  External — Marketplace Submission

# 1. Purpose and Scope

This document defines the MVP scope, acceptance criteria, and sprint plan for Canary LP's Square Marketplace submission. It is a working engineering contract: every feature listed here has a defined owner, testable acceptance criteria, and a gate that must pass before the feature is considered done.

The MVP is the minimum set of working software that earns Canary a Square Marketplace listing and delivers meaningful value to its first paying merchants. It is not a prototype. It is a production-grade, security-reviewed application that meets Square's technical and content standards.

Scope is Locked The MVP boundary defined in this document does not change without a joint decision by the Founder and the delivery team. Every idea that does not fit within this boundary is logged in the Scope Parking Lot (Section 7) and scheduled for a future sprint. Good ideas that arrive out of sequence are not ignored — they are parked and planned.

# 2. MVP Definition

The Canary MVP consists of four Epics. Each Epic represents a distinct layer of the product: the technical foundation, the core detection engine, the Square certification gate, and the initial case management workflow. All four must be complete before Canary submits to the Square App Marketplace.

| Epic | Name | Status | MVP Role |
| --- | --- | --- | --- |
| E0 | Platform Foundation | In Progress | The factory floor. Nothing else runs without this. |
| E1 | Core Fraud Detection — Chirp Engine | In Progress | The product. Real-time detection, alerts, merchant dashboard. |
| E2 | Square Marketplace Certification | Not Started | The business gate. Without this, Canary cannot be distributed. |
| E3 | Fox — Case Management Sprint 1 | Substantially Built | Differentiator. Turns an alert into a defensible, documented case. |

## Current Build Status

The codebase has been audited against all 97 MVP acceptance criteria. 27 are fully met, 14 are partially implemented, and 56 are not yet started. The overall MVP completion rate is approximately 28%.

| Epic | AC Total | ✓ Done | ~ Partial | ✗ Not Done | % |
| --- | --- | --- | --- | --- | --- |
| E0 Foundation | 23 | 4 | 5 | 14 | 17% |
| E1 Chirp Engine | 29 | 8 | 5 | 16 | 28% |
| E2 Certification | 23 | 1 | 1 | 21 | 4% |
| E3 Fox | 22 | 14 | 3 | 5 | 64% |
| TOTAL | 97 | 27 | 14 | 56 | ~28% |

Fox (E3) is the furthest along because its data model was designed from production LP standards and implemented with full evidentiary integrity from the start. E2 (Square Certification) is the critical path item — it is 4% complete and is the sole gate to Marketplace listing.

# 3. Sprint Plan — Path to Marketplace

The MVP ships in three sprints plus a pre-sprint foundation phase. Each sprint has a single, measurable goal. A sprint does not close until its goal is met — sprints do not slip their goal, they slip their date if necessary.

| Sprint | Goal | Target | Gate |
| --- | --- | --- | --- |
| Pre-Sprint — Foundation | Three-database architecture, RLS, Square OAuth, audit log hash chain — all running in Docker. | Active Now | Docker compose up in < 30 min |
| Sprint 1 — Fox + Hardening | Fox Case Management Sprint 1 complete. Chirp webhook HMAC and card fingerprint detection hardened. | Week of Feb 17 | All E3 AC passing; HMAC verified |
| Sprint 2 — Certification | All Square security requirements met. Application deployed to AWS production. Sandbox E2E test suite passing. | Week of Feb 24 | E2 AC complete; HTTPS live |
| Sprint 3 — Submission | Marketplace listing written, privacy policy and ToS live, 5 beta merchants confirmed, submission filed. | Week of Mar 2 | Submission filed with Square |
| Post-MVP — Phase 2+ | Goose (Bitcoin & Lightning), Owl (Analytics), Fox Sprint 2 (Ordinal minting), Clover integration. Scheduled after Square approval. | Q2 2026 | Square approval received |

# 4. MVP Feature Detail

Each MVP feature is listed below with its acceptance gate — the specific, testable condition that marks it complete. Features are grouped by Epic. No feature ships without its gate passing.

## Epic E0 — Platform Foundation

| ID | Feature | Status | Acceptance Gate |
| --- | --- | --- | --- |
| E0-F1 | Three-Database Architecture | Not Done | Three separate databases provisioned and running in Docker with connection tests passing on compose up. |
| E0-F2 | Multi-Tenant Row-Level Security | Not Done | Integration test confirms Merchant A cannot read Merchant B's data even with a direct DB query when session is scoped to Merchant A. |
| E0-F3 | Square OAuth Integration | Partial | Full OAuth flow works in sandbox. Access token and refresh token stored AES-256 encrypted. All required scopes present. |
| E0-F4 | Authentication & RBAC | Partial | Five roles enforced at API layer. Permission checks on every route. Login failures logged to audit_log. |
| E0-F5 | Immutable Audit Log | Partial | audit_log table is INSERT-only enforced by trigger. Hash chain implemented: each record's hash includes prior record hash. |

## Epic E1 — Chirp: Fraud Detection Engine

| ID | Feature | Status | Acceptance Gate |
| --- | --- | --- | --- |
| E1-F1 | Webhook Ingestion Pipeline | Partial | HMAC-SHA256 signature verification active on every incoming Square webhook. No unverified event processed. |
| E1-F2 | Chirp Detection Engine | Partial | All four detection rules use card fingerprint (not card last-4) for velocity checks. Rules are configurable per-merchant via DB. |
| E1-F3 | Alert Dashboard & SMS | Partial | Full alert status lifecycle (open → acknowledged → investigating → resolved → false_positive). Twilio SMS fires within 30 seconds on HIGH/CRITICAL. |
| E1-F4 | Natural Language Query | Done | Query engine handles 15+ patterns. Plain English responses with supporting data table. Audit logged. |
| E1-F5 | Card Risk Profiling | Not Done | card_profiles table populated on every webhook. Risk score (0–100) computed and stored. Blocked cards trigger CRITICAL alert within 5 seconds. |

## Epic E2 — Square Marketplace Certification

E2 is the critical path. It is 4% complete and is the sole gate to Marketplace listing. Every E2 feature must be done before the submission can be filed.

| ID | Feature | Status | Acceptance Gate |
| --- | --- | --- | --- |
| E2-F1 | Security & Compliance Hardening | Not Done | All environment variables validated at startup. HTTPS enforced. TLS certificate valid. No API keys in code or git history. Privacy policy and ToS URLs live. |
| E2-F2 | Production Deployment (AWS) | Not Done | Application running on AWS (EC2 + RDS). CI/CD pipeline active. Automated daily backups. Load balancer configured for zero-downtime deploys. |
| E2-F3 | Sandbox E2E Validation | Partial | Full E2E test chain passing: OAuth install → webhook → Chirp alert → dashboard → receipt detail → alert resolution. Five beta merchants active. |
| E2-F4 | Marketplace Listing & Submission | Not Done | Listing complete with 3+ screenshots, pricing, support URL. App passes Square automated and manual review. Filed and approved. |

## Epic E3 — Fox: Case Management Sprint 1

| ID | Feature | Status | Acceptance Gate |
| --- | --- | --- | --- |
| E3-F1 | Incident Report & Case Creation | Done | Structured case creation from alert with pre-populated fields. 17-type taxonomy. Case number auto-generated. All fields logged to timeline. |
| E3-F2 | Evidence Locker & Chain of Custody | Partial | INSERT-only evidence table enforced by DB trigger. SHA-256 hash on every upload. Hash verified on every retrieval. Every access logged. |
| E3-F3 | Case Timeline & Audit Trail | Done | Append-only timeline auto-populated on every state change. All entries include actor, timestamp, metadata. Timeline displayed newest-first. |
| E3-F4 | Case Actions & Resolution | Partial | All action types implemented. Status transitions logged. Case closure requires resolution note (min 10 characters). Closed cases are read-only. |

# 5. Quality Gate — Definition of Done

A feature is done when — and only when — all of its acceptance criteria are verified. Verification is performed by an independent QA review, not by the developer who built it. Self-certification is not accepted.

## The Gate Has Four Checks

- Acceptance Criteria: Every AC item for the feature is verified as passing. No partial credit. A feature is 100% done or it is not done.

- Security Review: Any feature that touches authentication, data storage, API communication, or webhook handling is reviewed against the Square Marketplace security requirements before it is marked done.

- Audit Coverage: Every state-changing operation in the feature writes to the audit_log before returning a success response. This is verified by test, not by code inspection.

- Documentation Gate: No feature is marked done without corresponding documentation: API endpoint documented, merchant-facing behavior described in plain language, any configuration options noted.

No Retrofitting Square Marketplace certification requirements are not a checklist applied at the end of the build. HTTPS enforcement, HMAC verification, encrypted credential storage, and Row-Level Security are built into the architecture from the first sprint. The approach is: if it is a requirement for certification, it is a requirement for development.

# 6. Critical Path to Marketplace

Three items on the critical path will determine the submission date. All three are Sprint 2 items. They cannot be parallelised — each depends on the previous.

| Item | Blocks | Sprint | Why It's Critical |
| --- | --- | --- | --- |
| HMAC-SHA256 Webhook Signature Verification | E2-F3 (sandbox E2E), E2-F4 (submission) | Sprint 1 | Square's automated technical check will fail without this. Submission is blocked. |
| AWS Production Deployment + HTTPS | E2-F1 (security), E2-F3 (E2E), E2-F4 (submission) | Sprint 2 | Square requires a production URL with valid TLS. Localhost does not qualify. |
| 5 Active Beta Merchants (Square Sandbox) | E2-F4 (submission) | Sprint 2 | Square requires documented evidence of active beta usage before manual review begins. |
| Privacy Policy + Terms of Service URLs | E2-F4 (submission) | Sprint 2 | Both URLs must be live on the production domain before the listing can be submitted. |

# 7. Scope Parking Lot

The following features were raised during the planning process and are real, planned capabilities. They are not in MVP scope. They are logged here — not discarded — and will be scheduled for post-MVP sprints after the Square Marketplace listing is confirmed.

| Feature | Earliest Sprint | Description |
| --- | --- | --- |
| Goose: Bitcoin & Lightning Payments | Q2 2026 | BTCPay Server integration, Lightning Network payment acceptance, LNURL-auth passwordless login, sat-denominated subscription billing. |
| Owl: Analytics Oracle | Q2 2026 | Total Retail Loss dashboard aggregating shrink, fraud, and operational loss data. Benchmarked against industry averages. |
| Fox Sprint 2: Chain of Custody Ordinals | Q3 2026 | Bitcoin Ordinal minting for evidence packets. Tamper-proof, blockchain-timestamped chain of custody for law enforcement and insurance use. |
| Square Ecosystem Deepening | Q3 2026 | Square for Restaurants, Square for Retail, Teams API, Appointments integration. Vertical-specific fraud rules. |
| Agentic Threat Defense | Q3 2026 | Behavioral fingerprinting, bot and CUA detection for agentic fraud, synthetic identity clustering, QR code HMAC tamper detection. |
| Multi-POS Abstraction (Clover) | Post-Approval | Canonical transaction schema enabling Clover and future POS integrations. Platform-agnostic architecture established before any Clover development begins. |

# 8. Contact and Submission Information

Canary LP is a product of GrowDirect. For questions related to this submission, scope clarification, or security review requests, please contact the Canary team directly.

| Item | Detail |
| --- | --- |
| Product Name | Canary LP — Early Warning Loss Prevention |
| Parent Company | GrowDirect |
| Square SDK Version | Square Python SDK v44+ |
| APIs Used | OAuth 2.0, Payments API, Webhooks API, Orders API |
| Tech Stack | Python 3.10+ / Flask / PostgreSQL / AWS / Docker |
| Document Version | v1.0 — February 2026 |

Canary LP  |  GrowDirect  |  Confidential  |  MVP Scope & Sprint Plan v1.0  |  February 2026