## gap_inventory
ISO 27001:2022 Annex A — 93 Control Gap Inventory
Ctrl | Title | Theme | DriftPOS-block? | Current state | Severity | Hours | Cost ($) | Weeks | Notes/owner
5.1 | Policies for information security | Org |  | absent | gap | 40 | 8000 | 0.44444 | No formal info-sec policy. Need to write one.
5.2 | Information security roles and responsibilities | Org |  | weak | gap | 16 | 3200 | 0.17778 | Roles informally held; not documented.
5.3 | Segregation of duties | Org |  | weak | partial | 16 | 3200 | 0.17778 | Senior engineers do everything; needs separation of admin from audit.
5.4 | Management responsibilities | Org |  | weak | partial | 24 | 4800 | 0.26667 | Owner is leader; need formal management commitment.
5.5 | Contact with authorities | Org |  | weak | partial | 8 | 1600 | 0.088889 | Knows local LE; needs documented contact list.
5.6 | Contact with special interest groups | Org |  | absent | gap | 8 | 1600 | 0.088889 | Not part of any infosec community.
5.7 | Threat intelligence | Org |  | absent | gap | 16 | 3200 | 0.17778 | No threat-intel program.
5.8 | Information security in project management | Org |  | weak | partial | 8 | 1600 | 0.088889 | Project mgmt informal; security not embedded.
5.9 | Inventory of information and other associated assets | Org |  | weak | gap | 40 | 8000 | 0.44444 | No formal asset inventory; deploy GCP CAI.
5.10 | Acceptable use of information and other associated assets | Org |  | absent | gap | 8 | 1600 | 0.088889 | Need AUP for staff and customers.
5.11 | Return of assets | Org |  | moderate | partial | 8 | 1600 | 0.088889 | Returns hardware on off-boarding; not documented.
5.12 | Classification of information | Org |  | absent | gap | 16 | 3200 | 0.17778 | No data classification scheme.
5.13 | Labeling of information | Org |  | absent | gap | 8 | 1600 | 0.088889 | No labeling.
5.14 | Information transfer | Org |  | weak | partial | 16 | 3200 | 0.17778 | Transfers happen via email; need governance.
5.15 | Access control | Org | YES | moderate | partial | 32 | 6400 | 0.35556 | Counterpoint has access control; modernization needs IAM.
5.16 | Identity management | Org |  | weak | partial | 24 | 4800 | 0.26667 | Identity is per-system; need lifecycle process.
5.17 | Authentication information | Org | YES | moderate | partial | 24 | 4800 | 0.26667 | Passwords/keys handled informally.
5.18 | Access rights | Org |  | weak | partial | 16 | 3200 | 0.17778 | Provisioning ad-hoc; de-provisioning has gaps.
5.19 | Information security in supplier relationships | Org |  | absent | gap | 16 | 3200 | 0.17778 | No vendor risk mgmt.
5.20 | Addressing info-sec within supplier agreements | Org |  | weak | partial | 16 | 3200 | 0.17778 | Some vendor contracts have security clauses; not all.
5.21 | Managing info-sec in the ICT supply chain | Org |  | absent | gap | 16 | 3200 | 0.17778 | Supply chain risk not analyzed.
5.22 | Monitoring/review/change mgmt of supplier services | Org |  | absent | gap | 16 | 3200 | 0.17778 | No vendor monitoring program.
5.23 | Information security for use of cloud services | Org | YES | absent | gap | 32 | 6400 | 0.35556 | Cloud governance from scratch — Org policies needed.
5.24 | IS incident management planning and preparation | Org | YES | weak | partial | 24 | 4800 | 0.26667 | Informal IR; need plan + tabletop.
5.25 | Assessment and decision on info-sec events | Org |  | absent | gap | 16 | 3200 | 0.17778 | No event triage process.
5.26 | Response to info-sec incidents | Org |  | weak | partial | 16 | 3200 | 0.17778 | Responds to incidents reactively; need process.
5.27 | Learning from info-sec incidents | Org |  | weak | partial | 8 | 1600 | 0.088889 | Postmortems happen verbally; not documented.
5.28 | Collection of evidence | Org |  | weak | gap | 16 | 3200 | 0.17778 | No forensic-readiness.
5.29 | Information security during disruption | Org |  | weak | partial | 16 | 3200 | 0.17778 | BCP exists for ops continuity, lacks infosec dimension.
5.30 | ICT readiness for business continuity | Org |  | moderate | partial | 24 | 4800 | 0.26667 | Backups exist; DR drills informal.
5.31 | Legal/statutory/regulatory/contractual requirements | Org |  | moderate | partial | 16 | 3200 | 0.17778 | Tax/PCI compliance tracked; broader regs less so.
5.32 | Intellectual property rights | Org |  | moderate | partial | 8 | 1600 | 0.088889 | IP policies for own work; not for customer customizations.
5.33 | Protection of records | Org |  | moderate | partial | 16 | 3200 | 0.17778 | Records kept; retention policy informal.
5.34 | Privacy and protection of PII | Org | YES | weak | partial | 32 | 6400 | 0.35556 | PII handled per-customer convention; need centralized policy.
5.35 | Independent review of info-sec | Org |  | absent | gap | 0 | 0 | 0 | Will become external audit by Growdirect (this!) — $0 internal cost.
5.36 | Compliance with policies/rules/standards | Org |  | absent | gap | 16 | 3200 | 0.17778 | No compliance monitoring.
5.37 | Documented operating procedures | Org |  | weak | partial | 32 | 6400 | 0.35556 | Some procedures documented; SOPs incomplete.
6.1 | Screening | People |  | moderate | partial | 8 | 1600 | 0.088889 | Background checks done; not formalized.
6.2 | Terms and conditions of employment | People |  | moderate | partial | 8 | 1600 | 0.088889 | Employment contracts include some security obligations.
6.3 | Info-sec awareness, education and training | People |  | weak | gap | 24 | 4800 | 0.26667 | No formal awareness training; deploy LMS.
6.4 | Disciplinary process | People |  | weak | partial | 8 | 1600 | 0.088889 | Disciplinary process exists; not security-specific.
6.5 | Responsibilities after termination/change of employment | People | YES | weak | gap | 16 | 3200 | 0.17778 | Off-boarding inconsistent; need security checklist.
6.6 | Confidentiality or non-disclosure agreements | People |  | moderate | compliant | 0 | 0 | 0 | NDAs in place — typical for a 20-year VAR.
6.7 | Remote working | People |  | weak | partial | 16 | 3200 | 0.17778 | Remote work informal; need policy + IAP.
6.8 | Information security event reporting | People |  | weak | partial | 8 | 1600 | 0.088889 | Reporting channel exists; not formalized.
7.1 | Physical security perimeters | Physical |  | moderate | partial | 8 | 1600 | 0.088889 | Office locked; basic perimeter.
7.2 | Physical entry | Physical |  | moderate | partial | 8 | 1600 | 0.088889 | Badge/key access; works.
7.3 | Securing offices, rooms and facilities | Physical |  | moderate | partial | 8 | 1600 | 0.088889 | Server room locked.
7.4 | Physical security monitoring | Physical |  | weak | partial | 8 | 1600 | 0.088889 | Cameras at office; not 24/7 monitored.
7.5 | Protecting against physical/environmental threats | Physical |  | moderate | partial | 8 | 1600 | 0.088889 | Standard fire/HVAC; no formal threat model.
7.6 | Working in secure areas | Physical |  | moderate | partial | 4 | 800 | 0.044444 | Server room procedures exist informally.
7.7 | Clear desk and clear screen | Physical |  | weak | partial | 4 | 800 | 0.044444 | Clear desk policy informal.
7.8 | Equipment siting and protection | Physical |  | moderate | partial | 4 | 800 | 0.044444 | Equipment sited reasonably.
7.9 | Security of assets off-premises | Physical |  | weak | partial | 8 | 1600 | 0.088889 | Off-premises asset controls weak.
7.10 | Storage media | Physical |  | weak | partial | 8 | 1600 | 0.088889 | Storage media disposal informal.
7.11 | Supporting utilities | Physical |  | moderate | partial | 4 | 800 | 0.044444 | Standard utilities; no redundancy beyond stock.
7.12 | Cabling security | Physical |  | moderate | partial | 4 | 800 | 0.044444 | Cabling reasonable; not formally secured.
7.13 | Equipment maintenance | Physical |  | moderate | compliant | 0 | 0 | 0 | Maintenance happens; no formal procedures needed for this scale.
7.14 | Secure disposal or re-use of equipment | Physical |  | weak | partial | 8 | 1600 | 0.088889 | Disposal informal; need formal sanitization process.
8.1 | User end point devices | Tech |  | weak | gap | 40 | 8000 | 0.44444 | No EDR/MDM. Deploy CrowdStrike + Workspace MDM.
8.2 | Privileged access rights | Tech | YES | weak | gap | 32 | 6400 | 0.35556 | Privileged access ad-hoc; deploy Cloud IAM + PAM.
8.3 | Information access restriction | Tech |  | weak | gap | 24 | 4800 | 0.26667 | Access enforcement weak; tighten with VPC-SC + IAM.
8.4 | Access to source code | Tech |  | moderate | partial | 16 | 3200 | 0.17778 | Source code in private GitHub; access controls informal.
8.5 | Secure authentication | Tech | YES | weak | gap | 32 | 6400 | 0.35556 | No MFA enforcement. Deploy Cloud Identity 2SV org-wide.
8.6 | Capacity management | Tech |  | moderate | partial | 16 | 3200 | 0.17778 | Capacity reactive; deploy Cloud Monitoring.
8.7 | Protection against malware | Tech |  | weak | partial | 16 | 3200 | 0.17778 | Workstation AV present; no centralized management.
8.8 | Management of technical vulnerabilities | Tech |  | weak | gap | 32 | 6400 | 0.35556 | No vuln scanning. Deploy Container Analysis + Wiz.
8.9 | Configuration management | Tech | YES | absent | gap | 64 | 12800 | 0.71111 | No IaC. Stand up Terraform + Config Connector.
8.10 | Information deletion | Tech |  | weak | partial | 16 | 3200 | 0.17778 | Deletion processes ad-hoc.
8.11 | Data masking | Tech |  | absent | gap | 24 | 4800 | 0.26667 | No data masking. Deploy DLP API for non-prod.
8.12 | Data leakage prevention | Tech |  | absent | gap | 32 | 6400 | 0.35556 | No DLP. Deploy DLP API + Workspace controls.
8.13 | Information backup | Tech | YES | moderate | partial | 24 | 4800 | 0.26667 | Backups exist; no recovery test. Add cross-region + drill.
8.14 | Redundancy of information processing facilities | Tech |  | weak | partial | 24 | 4800 | 0.26667 | Single-zone DBs; need HA + DR setup.
8.15 | Logging | Tech | YES | weak | gap | 32 | 6400 | 0.35556 | Logs scattered. Centralize on Cloud Logging + sinks.
8.16 | Monitoring activities | Tech | YES | absent | gap | 40 | 8000 | 0.44444 | No SIEM. Deploy SCC Premium + Chronicle.
8.17 | Clock synchronization | Tech |  | moderate | compliant | 0 | 0 | 0 | Use GCP-managed NTP; no work needed.
8.18 | Use of privileged utility programs | Tech |  | weak | partial | 16 | 3200 | 0.17778 | Admin tooling informal; deploy IAP + session recording.
8.19 | Installation of software on operational systems | Tech |  | weak | partial | 24 | 4800 | 0.26667 | Software install controls informal.
8.20 | Networks security | Tech | YES | weak | gap | 40 | 8000 | 0.44444 | Network security from scratch in cloud. VPC + Cloud Armor.
8.21 | Security of network services | Tech |  | weak | partial | 16 | 3200 | 0.17778 | Network services controls weak.
8.22 | Segregation of networks | Tech |  | weak | gap | 24 | 4800 | 0.26667 | No segmentation. Plan VPC + tenant isolation.
8.23 | Web filtering | Tech |  | weak | partial | 16 | 3200 | 0.17778 | Web filtering minimal; deploy Cloud DNS Forwarder.
8.24 | Use of cryptography | Tech | YES | weak | gap | 40 | 8000 | 0.44444 | Encryption inconsistent. Deploy Cloud KMS comprehensively.
8.25 | Secure development life cycle | Tech | YES | absent | gap | 56 | 11200 | 0.62222 | No formal SDLC. Deploy Cloud Build + Binary Auth.
8.26 | Application security requirements | Tech |  | weak | partial | 16 | 3200 | 0.17778 | App security requirements informal.
8.27 | Secure system architecture/engineering principles | Tech |  | weak | partial | 24 | 4800 | 0.26667 | Architecture review informal.
8.28 | Secure coding | Tech |  | weak | partial | 16 | 3200 | 0.17778 | Coding standards exist; not security-focused.
8.29 | Security testing in development and acceptance | Tech |  | absent | gap | 40 | 8000 | 0.44444 | No SAST/DAST. Deploy Web Security Scanner + Snyk.
8.30 | Outsourced development | Tech |  | moderate | compliant | 0 | 0 | 0 | No outsourced dev typical for this scale.
8.31 | Separation of dev/test/prod environments | Tech |  | weak | partial | 24 | 4800 | 0.26667 | Env separation informal. Formalize with Org/Folder structure.
8.32 | Change management | Tech |  | weak | partial | 16 | 3200 | 0.17778 | Change mgmt informal; deploy Cloud Build + IaC review.
8.33 | Test information | Tech |  | weak | partial | 16 | 3200 | 0.17778 | Test data handling informal.
8.34 | Protection of info systems during audit testing | Tech |  | moderate | compliant | 0 | 0 | 0 | Standard practice; no special audit-time work needed.
TOTAL | [5 empty] | 1684 | 336800 | 18.7111
DriftPOS-blocking subset | [5 empty] | 520 | 104000 | 9.6296
By theme:
Org | [5 empty] | 664 | 132800
People | [5 empty] | 88 | 17600
Physical | [5 empty] | 84 | 16800
Tech | [5 empty] | 848 | 169600

## severity_legend
Severity legend (input options for column F)
Value | Meaning
compliant | Control is fully met. Evidence exists. No remediation required.
partial | Control is partially met. Some evidence exists; gaps in either coverage or documentation.
gap | Control is not met. Remediation required before certifiable posture.
unknown | Current state not yet known. Discovery item for next iteration.
Current-state options (input column E):
Value | Meaning
strong | Native control in place; evidence-ready
moderate | Control in place but documentation gaps or partial coverage
weak | Practice exists but no formal control or evidence
absent | No practice; full implementation needed
unknown | Discovery required

## assumptions
Workload Estimator Assumptions
Assumption | Value | Notes
Loaded engineering rate ($/hr) | 200 | Should match cost-model loaded rate
Effective FTE count for ISO remediation | 3 | How many FTEs working on Phase 2 in parallel
Effective hours per FTE-week | 30 | 40 nominal − 25% overhead
Compliance-pressure factor (for valuation discount) | 70% | See valuation-impact-formulas Formula 1
Skill version | saas-acquisition-diligence v1.0
Linked cost-model run | {path to cost-model-output.xlsx} | Cross-reference

## valuation_impact
Valuation Impact — Gap-to-discount math
Line | Best ($) | Expected ($) | Worst ($)
Total ISMS-gap remediation cost (linked from gap_inventory) | 235760 | 336800 | 505200
Compliance-pressure factor | 50% | 70% | 100%
Discount-for-ISMS-gap (price reduction) | 117880 | 235760 | 505200