MASTER SERVICES AGREEMENT
EXHIBIT A – FORM STATEMENT OF WORK

STATEMENT OF WORK NO. _____

This Statement of Work No. ___ (“Statement of Work”) is entered into as of ________, 20___, (“Effective Date”) by and between TJX and [The Retail Equation] (“Service Provider”) and is subject to that certain Master Services Agreement between the parties dated ________, 20___ (the “Agreement”). All capitalized terms not otherwise defined herein, shall have the meanings ascribed to them in the Agreement.

- Description of Services.

The scope for this Statement of Work includes the activities which will be required to install Appriss Retail Secure Store 5 application for TJX Europe in a hosted configuration.  The TJX Europe data for all locations in the the United Kingdom, Republic of Ireland, Germany, Poland, Austria and Netherlands will be collocated with the TJX North America data in the existing application environment containing thirteen (13) months of rolling data.  The Secure application will be configured to manage the growth rate of TJX as outlined in the Order Form.

In addition to the installation of the base application Appriss Retail will work with TJX Europe to establish the following integration elements:

- A single daily feed of Point of Sale (POS) transactional data including all register activity from corporately owned retail outlets including completed e-commerce transactions delivered the same format and schema as sales from POS.

- Store Master data feed of location hierarchy and store attributes.

- Item Master data feed of merchandise hierarchy and product attributes.

- Human Resources Associate data feed.

- Integration of a single Reticketing system file containing information about price tickets issued in store.

- Integration of a single Markdown system file containing information about price changes taken at store level.

- Integration of a CAP Index file to be linked to the location file as an attribute of retail locations.

- Integration of a single file containing supplementary gift card information from a third-party gift card provider.

- Integration of a single file containing location Shrink data

- Integration of a file containing Verify Returns decisions to be joined to the POS tlog data

- Integration of a single file containing details of Self-Service Checkout interventions

- Integration of single file format for Employee Clock data collected at store level.

- Integration of an ecommerce risk score file

- Integration of the Secure Investigations area to a third party Case Management solution

During the initiation phase of the project, Appriss Retail will work with TJX Europe to provide a walk through of general operational processes alongside with the POS data and supplemental feeds review to ensure core metrics and data points that indicate potential fraudulent activity or process issues will be included in the data feeds provided. Appriss Retail will provide directions on a recommended standard data layout and will work with TJX Europe to define a risk data requirements mapping definition document used as the basis for all development and configuration efforts.

This project will include developing a data transport and load mechanism to process up to thirteen (13) months of historical data as long as TJX Europe can provide this data in the same format as ongoing operation data feeds prior to go live.  Appriss Retail consultants will assist TJX Europe in defining the corporate risk dictionary for identifying fraud in the organization, configure the Secure Store Application per TJX Europe Business requirements, and provide training on the application prior to go-live.

The Secure Training Program delivered by Appriss Retail Client Success staff will consist of the following general elements (specific requirements and timing will be agreed between both parties during the project):

- A series of strategy calls will be held with the TJX Europe core business user team to identify foundational target metrics.  The first call is a demo of Secure and supplemental calls are designed to progressively develop the foundational metric strategy.

- TJX Europe system admins and analysts must be provided access to the Appriss EBR system as soon as sample data has been delivered to Appriss by TJX Europe.  The intention is to complete the implementation using an Agile methodology where TJX Europe is providing incremental feedback through multiple iterations of the implementation.  As such, TJX Europe users will receive introductory training in the basics of executing and building searches as early as possible in the implementation.  End users will be provided access to the test environment after the Data Validation session, as a means of continuing the validation process and increasing their knowledge of the use of Secure.

- Calls will be scheduled weekly throughout the course of the implementation to answer questions regarding the use of Secure and to discuss observations.

- Onsite training will consist of one day training for admin users with an additional two days of end user training and workshops in the use of Secure and analytics best practices and strategies.

- After completion of the above items, the Client Success department will continue to support/mentor the TJX Europe business users through ongoing calls and screen sharing meetings, which can be scheduled as needed.  The Client Success team is a resource for the business users to not only assist in the growth of their proficiency in the use of Secure, but to also assist in the continued development of metrics and strategies in the Secure application.

- Schedule. [Insert the schedule of dates during which Services are provided]

|  | Secure EBR - Typical Example of Implementation Milestones |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Milestone | Assigned | Total number of days | Start week (e.g wk 0) | End week (e.g wk 4) |
|  | Project Planning |  |  |  |  |
|  | Create SOW | PM |  | Wk 1 | Wk 1 |
|  | Create Draft Plan | PM |  | Wk 1 | Wk 1 |
|  | Re-distribute Project Plan | PM |  | Wk 1 | Wk 1 |
|  | Create Solution Acceptance Criteria | PM/Client Success |  | Wk 1 | Wk 1 |
|  | Project Kick-Off | PM/Client Success/Delivery/Client |  | Wk 1 | Wk 1 |
|  | Set Up Weekly Governance Meeting - External | PM |  | Wk 1 | Wk 1 |
|  | Set Up Weekly Governance Meeting - Client Success | Client Success |  | Wk 1 | Wk 1 |
|  | Total number of days |  | 4 |  |  |
|  | Pre-requisites |  |  |  |  |
|  | Sample POS Data Provided | Client |  | Wk1 | Wk2 |
|  | Sample Reference Data Provided | Client |  | Wk1 | Wk2 |
|  | POS Documentation Received | Client |  | Wk1 | Wk2 |
|  | Total number of days |  | 4 |  |  |
|  | Analysis Phase |  |  |  |  |
|  | Client Success Site Visit | Client Success/Client |  | Wk3 | Wk6 |
|  | Create Risk Workbook 1 | Client Success/Client |  | Wk3 | Wk6 |
|  | Create Issue Tracker | Client Success |  | Wk3 | Wk6 |
|  | Create Master Mapping Document | Delivery |  | Wk3 | Wk6 |
|  | Map POS Data to the Secure CRDM Data Model | Delivery |  | Wk3 | Wk6 |
|  | Map Reference Data to CRDM (Stores, Product Hierarchy etc) | Delivery |  | Wk3 | Wk6 |
|  | Total number of days |  | 25 |  |  |
|  | Design Phase |  |  |  |  |
|  | Design Meeting: Data load, Frequency, Transport | Delivery |  | Wk7 | Wk8 |
|  | Estimate storage requirements - QA Environment | Delivery/PM |  | Wk7 | Wk8 |
|  | Estimate hardware requirements - QA Environment | Delivery/PM |  | Wk7 | Wk8 |
|  | Create Solution Design - Discourse | Delivery |  | Wk7 | Wk8 |
|  | Submit Environment Requests - QA Environment | Delivery/PM |  | Wk7 | Wk8 |
|  | Total number of days |  | 11 |  |  |
|  | Development & Configuration |  |  |  |  |
|  | Setup QA Test Environment | Infrastructure |  | Wk3 | Wk10 |
|  | Build POS Data Feed (RTI POS Loader) | Delivery |  | Wk3 | Wk10 |
|  | Build Reference Data Interfaces (Stores, Product Hierarchy etc) | Delivery |  | Wk3 | Wk10 |
|  | Packaging & Release Notes - Discourse | Delivery |  | Wk3 | Wk10 |
|  | Update CRDM Master Mapping Document | Delivery |  | Wk3 | Wk10 |
|  | Total number of days |  | 53 |  |  |
|  | Solution Testing |  |  |  |  |
|  | Install Secure Solution into Test | Delivery |  | Wk9 | Wk12 |
|  | Upgrade to Secure 3.6 | Delivery |  | Wk9. | Wk12 |
|  | Integration Testing - Test | Delivery |  | Wk9 | Wk12 |
|  | Receive Tlog & Reference Data files on SFTP | Delivery/Client |  | Wk9 | Wk12 |
|  | End to End Test TLOG Load Process | Delivery/Client |  | Wk9. | Wk12 |
|  | End to End Test Other Data Feeds | Delivery/Client |  | Wk9 | Wk12 |
|  | Whitelist IP Addresses | PM/Delivery |  | Wk9 | Wk12 |
|  | Volume & Performance Testing - Test Environment | Delivery |  | Wk9 | Wk12 |
|  | POS Load Testing - Test Environment | Delivery |  | Wk9 | Wk12 |
|  | Total number of days |  | 25 |  |  |
|  | Pre-UAT Testing 2 |  |  |  |  |
|  | Pre-UAT Testing Phase 1 | Delivery/Client Success |  | Wk9 | Wk12 |
|  | Pre-UAT Phase 1 Defect Resolution | Delivery/Client Success |  | Wk9 | Wk12 |
|  | Pre-UAT Testing Phase 2 | Delivery/Client Success |  | Wk9 | Wk12 |
|  | Pre-UAT Phase 2 Defect Resolution | Delivery/Client Success |  | Wk9 | Wk12 |
|  | Secure Application, Questions, Monitors, Maintenance, Reports | Delivery/Client Success |  | Wk9 | Wk12 |
|  | Configure Questions and Monitors | Delivery/Client Success |  | Wk9 | Wk12 |
|  | System Configuration (User Roles, Metadata Naming, Portal Page) | Delivery/Client Success |  | Wk9 | Wk12 |
|  | Total number of days |  | 11 |  |  |
|  | Environment preparation | Delivery/PM |  |  |  |
|  | Estimate storage requirements - Production Environment | Delivery |  | Wk12 | Wk12 |
|  | Estimate hardware requirements - Production Environment | Delivery |  | Wk12 | Wk12 |
|  | Submit Production Environment Request | Delivery |  | Wk12. | Wk12 |
|  | Total number of days |  | 1 |  |  |
|  | Implementation | Delivery |  |  |  |
|  | Build Production Environment | Infrastructure |  | Wk13 | Wk14 |
|  | Test Access & Connectivity | Delivery |  | Wk13 | Wk14 |
|  | Install Secure Solution into Production | Delivery |  | Wk13 | Wk14 |
|  | Total number of days |  | 11 |  |  |
|  | SIT & Performance Testing | Delivery |  |  |  |
|  | Volume & Performance Testing - Production | Support |  | Wk15 | Wk16 |
|  | POS Load Testing - Production Environment | Delivery |  | Wk15 | Wk16 |
|  | Secure Application, Questions, Monitors, Maintenance, Reports | Delivery |  | Wk15 | Wk16 |
|  | Total number of days |  | 11 |  |  |
|  | Training & UAT Testing 3 | Client/Client Success Delivery |  |  |  |
|  | User Training Session 1 (ON SITE) | Client Success/Client |  | Wk13 | Wk18 |
|  | UAT Testing 1 (ONSITE) | Client Success/Client |  | Wk13 | Wk18 |
|  | Defect Resolution | Client Success/Delivery |  | Wk13 | Wk18 |
|  | User Training Session 2 (ON SITE) | Client Success/Client |  | Wk13 | Wk18 |
|  | Defect Resolution | Client Success/Delivery |  | Wk13 | Wk18 |
|  | Question/Monitor Tuning | Client Success/Delivery |  | Wk13 | Wk18 |
|  | Solution Acceptance Meeting | Client Success/Client/PM |  | Wk13 | Wk18 |
|  | Total number of days |  | 39 |  |  |
|  | Support HyperCare | Support/Delivery |  |  |  |
|  | Initial Handover to Support | Delivery |  | Wk11 | Wk18 |
|  | Discourse | Delivery/Support |  | Wk11 | Wk18 |
|  | Roles & Responsabilities - Communication | Support |  | Wk11 | Wk18 |
|  | PRTG | Support |  | Wk11 | Wk18 |
|  | Issues Logged in CRM | Support |  | Wk11 | Wk18 |
|  | Support Accounts | Support |  | Wk11 | Wk18 |
|  | Total Number of Days |  | 53 |  |  |
|  | Handover To Support - GO LIVE |  |  |  |  |
|  | Solution Support Guide - Discourse | PM/Delivery/Support |  |  |  |
|  | Support Handover - Support Desk | PM/Delivery/Support |  |  |  |
|  | Total number of days |  | 3 |  |  |

- Deliverables. [Insert a detailed description of any Deliverables and any applicable Acceptance Criteria.

| Deliverable | Description | Responsible | Acceptance Criteria |
| --- | --- | --- | --- |
| - Risk Workbook | The formal relationship with Client Services begins with building the Risk Workbook – typically this takes place over a number of meetings – the first of which is where we build the Risk Areas – these are groups of behaviours that can be categorised into categories such as Refunds, Line Voids, Discounts etc. Following this we will discuss some of the detailed behaviours that are present or suspected to be present which will become Questions within Secure. | Appriss Client Services | - Mutually agreed risk work has been configured within the Secure Store Application |
| - Implementation Support | Participate in Implementation planning and execute Implementation activities as per plan | Appriss Delivery Team | - Users configured for production access. - Successful implementation as per agreed upon criteria in Implementation Plan |
| - User Acceptance Testing (“UAT”) Support | Engage with client to review UAT test strategy, plan and test script, facilitate testing process and fix defects identified in Consultant delivered code during User Acceptance Testing | Appriss Delivery Team | - All P0 and P1 defects identified during UAT are fixed per requirements and approved by client |
| - Training | Delivery of online training materials: User guides and quick start help guides for core application features and facilitate a train the trainer program to assist client with application roll out | Appriss Client Services | - Approved online training materials - Mutually agreed train the trainer program. |

- Fees. [Insert a detailed description of fees associated with Services and the methodology by which they are calculated (fixed rate, hourly, capped total)] and when due.

All Fees associated with this statement of work are documented in the Appriss TJX Europe Secure Store EBR Core Order From.

IN WITNESS WHEREOF the parties have executed this Statement of Services as of the Effective Date first above written.

| SERVICE PROVIDER By: Print Name: Title: Address: Date: | TJX EUROPE CORPORATION By: Print Name: Title: Address: 2401 Utah Avenue South, Seattle, WA 98134 Date: |
| --- | --- |